## Sheet1
Group Name | Team TAE (Trial and Error)
Roles
Members | Ayes, Mari Cris P. | Developer/CICD
| Cabrera, Anjhillian S. | CI/CD
| Narca, Cris Gievid M. | Team Leader
| Pineda, Pauleen S. | Documentation
| Robles, Joey Ann O. | Developer
Project Name | Project Simulation
Start Date | 2016-09-06
End Date | 2016-09-16
Overall Progress | 72.73%
Tasks | Responsible | Start | End | Status | 2016-09-06 | 2016-09-07 | 2016-09-08 | 2016-09-09 | 2016-09-13 | 2016-09-14 | 2016-09-15 | 2016-09-16 | Remarks
CI/CD
Set kick-off meeting | All | 2016-09-06 | 2016-09-06 | Complete | [8 empty] | Done
Agree on objectives | All | 2016-09-06 | 2016-09-06 | Complete | [8 empty] | Done
1. Provision Environment (Set-up)
a. Create a Stack | Cris Narca | 2016-09-07 | 2016-09-07 | Complete | [8 empty] | Done
b. Launch an Instance | Cris Narca | 2016-09-07 | 2016-09-07 | Complete | [8 empty] | Done
c. Install Docker | Mari Cris Ayes / Anjhilian Cabrera | 2016-09-07 | 2016-09-07 | Complete | [8 empty] | Done
d. Create and deploy Tomcat | Mari Cris Ayes / Anjhilian Cabrera | 2016-09-07 | 2016-09-07 | Complete | [8 empty] | Done
e. Documentation | Pauleen Pineda | 2016-09-07 | 2016-09-07 | Complete | [8 empty] | Done
2. Java Web App
a. Provide Project | Mari Cris Ayes/Joey Robles | 2016-09-07 | 2016-09-09 | Complete | [8 empty] | Done
3. Configurations in Jenkins
a. Gitlab to Jenkins | Mari Cris Ayes / Anjhilian Cabrera | 2016-09-07 | 2016-09-08 | Complete | [8 empty] | Done
b. Maven to Jenkins | Mari Cris Ayes / Anjhilian Cabrera | 2016-09-07 | 2016-09-08 | Complete | [8 empty] | Done
d. Sonarqube to Jenkins | Mari Cris Ayes / Anjhilian Cabrera | 2016-09-07 | 2016-09-08 | Complete | [8 empty] | Done
e. Ansible to Jenkins | Mari Cris/ Anjhilian/ Cris | 2016-09-08 | 2016-09-09 | Complete | [8 empty] | Done
f. Tomcat to Jenkins | Mari Cris Ayes / Anjhilian Cabrera | 2016-09-09 | 2016-09-13 | Complete | [8 empty] | Done
g. Selenium to Jenkins | Mari Cris Ayes / Anjhilian Cabrera | 2016-09-09 | 2016-09-14 | In progress | [8 empty] | NYD
4. Creation of Cartridges
a. Docker compose | Joey Robles | 2016-09-08 | 2016-09-14 | In progress | [8 empty] | NYD
b. Platform management | Pauleen Pineda | 2016-09-08 | 2016-09-14 | In progress | [8 empty] | NYD
c. Docker cartridges | Cris Narca | 2016-09-07 | 2016-09-14 | In progress | [8 empty] | NYD
5. Compile Documentation
a. Document step by step process of provisioning with screen shots. | Pauleen Pineda | 2016-09-08 | 2016-09-14 | In progress | [8 empty] | NYD
b. Document roles and responsibilities of each team member. | Pauleen Pineda | 2016-09-09 | 2016-09-09 | Complete | [8 empty] | Done
c. Document your workplan. | Pauleen Pineda | 2016-09-09 | 2016-09-15 | Complete | [8 empty] | Done
d. Document how SCM and CI works. | Pauleen Pineda | 2016-09-09 | 2016-09-15 | In progress | [8 empty] | NYD
Live Project Simulation |  | 2016-09-16 | 2016-09-16
Status | Remarks
Complete | Done
Overdue | NYD (Not Yet Done)
In progress | In progress
Not started | Not started