## Sheet1
Group Name | Team TAE (Trial and Error)
Roles
Members | Ayes, Mari Cris P. | CI/CD
| Cabrera, Anjhillian S. | CI/CD
| Narca, Cris Gievid M. | Team Leader
| Pineda, Pauleen S. | Documentation
| Robles, Joey Ann O. | Developer
Project Name | Project Simulation
Start Date | 2016-09-06
End Date | 2016-09-16
Overall Progress | 16.6%
Tasks | Responsible | Start | End | Duration | Status | 2016-09-06 | 2016-09-07 | 2016-09-08 | 2016-09-09 | 2016-09-13 | 2016-09-14 | 2016-09-15 | 2016-09-16 | Remarks
CI/CD
Set kick-off meeting |  | 2016-09-06 | 2016-09-06 | 0 | Complete
Agree on objectives |  | 2016-09-06 | 2016-09-06 | 0 | Complete
1. Set up
a. Provisioning Environment |  | 2016-09-07 | 2016-09-07 | 0 | Not started
b. ADOP Gen 5 Tools |  | 2016-09-07 | 2016-09-07 | 0 | Not started
2. Java Web App
a. Provide Project |  | 2016-09-08 | 2016-09-08 | 0 | Not started
3. Creation of Cartridges
a. Docker compose |  | 2016-09-08 | 2016-09-08 | 0 | Not started
b. Platform management |  | 2016-09-09 | 2016-09-09 | 0 | Not started
c. Docker cartridges |  | 2016-09-13 | 2016-09-13 | 0 | Not started
4. Document your project
a. Document step by step process of provisioning with screen shots. |  | 2016-09-14 | 2016-09-14 | 0 | Not started
b. Document roles and responsibilities of each team member. |  | 2016-09-14 | 2016-09-14 | 0 | Not started
c. Document your workplan. |  | 2016-09-15 | 2016-09-15 | 0 | Not started
d. Document how SCM and CI works. |  | 2016-09-15 | 2016-09-15 | 0 | Not started
Launch |  | 2016-09-16 | 2016-09-16
Status
Complete
Overdue
In progress
Not started